## Sheet1
Task | Start Date | End Date | Time Spent( Hrs) | Progress
Interacting with Team Mates | 13-03-2023 | 13-03-2023 | 2 | 100%
Project Idea Discussion | 13-03-2023 | 13-03-2024 | 10 | 100%
Abstract Discussion with Guide | 19-03-2023 | 13-03-2025 | 2 | 100%
Interacting with Team Mates | 20-03-2023 | 13-03-2026 | 2 | 100%
Research | 22-03-2023 | 13-03-2027 | 20 | 100%
SRS Document | 2023-02-04 | 13-03-2028 | 6 | 100%
Learning Required technologies | 2023-12-04 | 13-03-2029 | 60 | 80%
Review-1 | 2023-10-05 | 13-03-2030 | 1 | 100%
Choosing Domain for Implementation | 18-05-2023 | 13-03-2031 | 3 | 100%
Implementation of version -1 project using TURTLE | 19-05-2023 | 13-03-2032 | 20 | not supported
Document Preparation for Review - 2 | 2023-07-06 | 13-03-2033 | 2 | 100%
Review-2 | 16-06-2023 | 13-03-2034 | 1 | 100%
Implementation of version -2 Project using canvas | 17-06-2023 | 13-03-2035 | 50 | 70%
Implementation of version -2 Project | 2023-08-07 | 13-03-2036 | 30 | 100%
implementation of Interface | 2023-12-07 | 13-03-2037 | 7 | 100%
Integration of Interface and Assistant | 13-07-2023 | 13-03-2038 | 7 | 100%
Document Preparation for Final Review | 2023-12-07 | 13-03-2039 | 7 | 100%
Name | Roles | No.of lines of code written | Time Spent
G.Uday Sankar (S180443) | Project lead,Coding,Document Preparation,Research | 700 | 90
V.Sankara rao (S180681) | Coding,Document Preparation,Research | 350 | 70
T.Sai Kumar (S180020) | Research,Coding,Document Preparation | 350 | 70